## How to use
CAPITTANCE
S/4HANA Cutover Runbook — 214 steps
Nine tracks, timed to the minute, with an owner, verification evidence and a rollback path for every task.
How to use it
1. Replace T-0 with your go-live timestamp; every task start is an offset from T-0.
2. Replace owner roles with named people and a backup for each task.
3. Update the Status column hourly during the cutover (drop-down provided).
4. Hold the three Go/No-Go checkpoints on the 'Go-No-Go' sheet before the point of no return.
5. If a verification fails, execute the rollback path and escalate to the Cutover Manager.
Tracks
1. Governance & Go/No-Go — 20 steps · owner: Cutover Manager
2. Technical / Basis — 30 steps · owner: Basis Lead
3. Data Migration — 40 steps · owner: Data Migration Lead
4. Finance & Period-End — 28 steps · owner: Finance Lead
5. Integrations & Interfaces — 24 steps · owner: Integration Lead
6. Security & Access — 16 steps · owner: Security Lead
7. Business Readiness & Comms — 18 steps · owner: Change Lead
8. Legacy Freeze & Decommission — 14 steps · owner: Legacy Systems Lead
9. Hypercare Handover — 24 steps · owner: Hypercare Lead
Run this runbook live — with owners, alerts and a real-time cutover dashboard — at https://capittance.com

## Runbook
Step | Track | Phase | Planned start | Duration (min) | Task | Owner | Predecessor | Verification / evidence | Rollback path | Status
1 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-72:00 | 30 | Confirm cutover window and blackout calendar with business owners | Cutover Manager | — | Signed calendar in PMO folder | Re-baseline window; notify steerco | Not started
2 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-71:30 | 30 | Freeze cutover runbook version and publish to all track leads | Cutover Manager | 1 | Runbook vX.0 read-receipts | Revert to last approved version | Not started
3 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-71:00 | 30 | Open cutover command centre bridge (24x7 rota) | Cutover Manager | 2 | Bridge live, rota published | Fallback dial-in activated | Not started
4 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-70:30 | 30 | Confirm named owner and backup for every runbook task | Cutover Manager | 3 | Zero unassigned tasks | Escalate gaps to cutover manager | Not started
5 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-70:00 | 30 | Validate final mock cutover lessons are closed | Cutover Manager | 4 | Lessons log 100% closed | Hold Go decision | Not started
6 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-69:30 | 30 | Confirm production transport list frozen | Cutover Manager | 5 | Transport freeze ticket approved | Unfreeze with CAB approval | Not started
7 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-69:00 | 30 | Run Go/No-Go checkpoint 1 (readiness) | Cutover Manager | 6 | Steerco minutes | No-Go: invoke contingency plan | Not started
8 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-68:30 | 30 | Confirm hypercare rota and escalation matrix | Cutover Manager | 7 | Rota acknowledged by all | Extend project team on-call | Not started
9 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-68:00 | 30 | Brief executive sponsor on rollback criteria | Cutover Manager | 8 | Sponsor sign-off on criteria | n/a | Not started
10 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-67:30 | 30 | Confirm communications plan for go-live weekend | Cutover Manager | 9 | Comms schedule approved | Use holding statements | Not started
11 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-67:00 | 30 | Issue cutover start notification | Cutover Manager | 10 | Email sent to distribution list | Issue postponement notice | Not started
12 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-66:30 | 30 | Hourly status cadence started | Cutover Manager | 11 | Status log updated hourly | Escalate missed checkpoint | Not started
13 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-66:00 | 30 | Track critical path variance against plan | Cutover Manager | 12 | Variance < 2h | Trigger re-plan of downstream tasks | Not started
14 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-65:30 | 30 | Run Go/No-Go checkpoint 2 (data loaded) | Cutover Manager | 13 | Checkpoint minutes | No-Go: restore legacy as system of record | Not started
15 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-65:00 | 30 | Confirm point-of-no-return criteria met | Cutover Manager | 14 | All PONR criteria green | Execute rollback before PONR | Not started
16 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-64:30 | 30 | Run Go/No-Go checkpoint 3 (business verification) | Cutover Manager | 15 | Business sign-off sheet | No-Go: rollback per track plans | Not started
17 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-64:00 | 30 | Final Go decision recorded by executive sponsor | Cutover Manager | 16 | Signed Go decision | Execute full rollback runbook | Not started
18 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-63:30 | 30 | Issue go-live announcement | Cutover Manager | 17 | Announcement published | Issue delay communication | Not started
19 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-63:00 | 30 | Hand over command centre to hypercare lead | Cutover Manager | 18 | Handover checklist signed | Cutover manager retains control | Not started
20 | 1. Governance & Go/No-Go | Pre-cutover (T-72h to T-48h) | T-62:30 | 30 | Publish cutover close-out report | Cutover Manager | 19 | Report circulated to steerco | n/a | Not started
21 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-66:00 | 40 | Confirm production system sizing and HANA memory headroom | Basis Lead | — | Sizing report > 20% headroom | Scale up before cutover | Not started
22 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-65:20 | 40 | Verify production backup schedule and retention | Basis Lead | 21 | Last full backup restore-tested | Re-run full backup | Not started
23 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-64:40 | 40 | Take full pre-cutover backup of production | Basis Lead | 22 | Backup ID logged | Repeat backup | Not started
24 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-64:00 | 40 | Take snapshot of legacy ERP | Basis Lead | 23 | Snapshot ID logged | Repeat snapshot | Not started
25 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-63:20 | 40 | Lock non-cutover users in legacy ERP | Basis Lead | 24 | User lock report | Unlock users | Not started
26 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-62:40 | 40 | Suspend legacy batch jobs | Basis Lead | 25 | Job list shows suspended | Release jobs | Not started
27 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-62:00 | 40 | Import final transport queue to production | Basis Lead | 26 | STMS import log clean | Reverse transports from backup | Not started
28 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-61:20 | 40 | Run post-import consistency checks | Basis Lead | 27 | SICK / SGEN clean | Restore pre-import backup | Not started
29 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-60:40 | 40 | Configure production number ranges | Basis Lead | 28 | Number range report | Reset ranges | Not started
30 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-60:00 | 40 | Activate production output management | Basis Lead | 29 | Test output printed | Revert to legacy output | Not started
31 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-59:20 | 40 | Configure printers and spool servers | Basis Lead | 30 | Printer test pages | Use backup print server | Not started
32 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-58:40 | 40 | Configure background job schedule | Basis Lead | 31 | SM37 schedule matches plan | Remove scheduled jobs | Not started
33 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-58:00 | 40 | Configure SLD / RFC destinations | Basis Lead | 32 | RFC connection tests pass | Revert destinations | Not started
34 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-57:20 | 40 | Configure SSO and identity provider | Basis Lead | 33 | SSO test login succeeds | Fallback to password login | Not started
35 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-56:40 | 40 | Validate Fiori launchpad catalogues | Basis Lead | 34 | Catalogue smoke test | Restore launchpad config | Not started
36 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-56:00 | 40 | Validate system performance baseline | Basis Lead | 35 | Response times within SLA | Tune or scale | Not started
37 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-55:20 | 40 | Enable system monitoring and alerting | Basis Lead | 36 | Alerts firing to on-call | Manual monitoring rota | Not started
38 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-54:40 | 40 | Configure archive and retention rules | Basis Lead | 37 | Retention rules active | Disable rules | Not started
39 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-54:00 | 40 | Configure disaster recovery replication | Basis Lead | 38 | Replication lag < 15 min | Manual DR backup | Not started
40 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-53:20 | 40 | Validate network and firewall rules | Basis Lead | 39 | Port checks pass | Revert firewall change | Not started
41 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-52:40 | 40 | Validate VPN / remote access for hypercare | Basis Lead | 40 | Remote login tested | Onsite support | Not started
42 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-52:00 | 40 | Validate email / SMTP relay from S/4HANA | Basis Lead | 41 | Test email received | Revert SMTP config | Not started
43 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-51:20 | 40 | Run technical go-live health check | Basis Lead | 42 | Health check report green | Hold business access | Not started
44 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-50:40 | 40 | Take post-load backup of production | Basis Lead | 43 | Backup ID logged | Repeat backup | Not started
45 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-50:00 | 40 | Validate system clock / timezone settings | Basis Lead | 44 | Time sync confirmed | Correct NTP | Not started
46 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-49:20 | 40 | Confirm licences applied | Basis Lead | 45 | Licence check clean | Temporary licence | Not started
47 | 2. Technical / Basis | Pre-cutover (T-72h to T-48h) | T-48:40 | 40 | Clear test data from production client | Basis Lead | 46 | Clean-up report | Restore from backup | Not started
48 | 2. Technical / Basis | Cutover execution (T-48h to T-24h) | T-48:00 | 40 | Open production client for business users | Basis Lead | 47 | Client settings logged | Close client | Not started
49 | 2. Technical / Basis | Cutover execution (T-48h to T-24h) | T-47:20 | 40 | Unlock business users in S/4HANA | Basis Lead | 48 | User unlock report | Lock users | Not started
50 | 2. Technical / Basis | Cutover execution (T-48h to T-24h) | T-46:40 | 40 | Decommission cutover-only technical users | Basis Lead | 49 | User list clean | Re-enable temporarily | Not started
51 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-60:00 | 45 | Extract final Organisational structure & company codes from legacy | Data Migration Lead | — | Extract record count logged | Re-extract from snapshot | Not started
52 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-59:15 | 45 | Load Organisational structure & company codes into S/4HANA | Data Migration Lead | 51 | Load log: 0 errors | Delete loaded records and reload | Not started
53 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-58:30 | 45 | Reconcile Organisational structure & company codes (counts and values) | Data Migration Lead | 52 | Reconciliation within tolerance | Correct and reload delta | Not started
54 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-57:45 | 45 | Business sign-off on Organisational structure & company codes | Data Migration Lead | 53 | Data owner signature | Hold dependent loads | Not started
55 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-57:00 | 45 | Extract final GL accounts & chart of accounts from legacy | Data Migration Lead | 54 | Extract record count logged | Re-extract from snapshot | Not started
56 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-56:15 | 45 | Load GL accounts & chart of accounts into S/4HANA | Data Migration Lead | 55 | Load log: 0 errors | Delete loaded records and reload | Not started
57 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-55:30 | 45 | Reconcile GL accounts & chart of accounts (counts and values) | Data Migration Lead | 56 | Reconciliation within tolerance | Correct and reload delta | Not started
58 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-54:45 | 45 | Business sign-off on GL accounts & chart of accounts | Data Migration Lead | 57 | Data owner signature | Hold dependent loads | Not started
59 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-54:00 | 45 | Extract final Cost & profit centres from legacy | Data Migration Lead | 58 | Extract record count logged | Re-extract from snapshot | Not started
60 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-53:15 | 45 | Load Cost & profit centres into S/4HANA | Data Migration Lead | 59 | Load log: 0 errors | Delete loaded records and reload | Not started
61 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-52:30 | 45 | Reconcile Cost & profit centres (counts and values) | Data Migration Lead | 60 | Reconciliation within tolerance | Correct and reload delta | Not started
62 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-51:45 | 45 | Business sign-off on Cost & profit centres | Data Migration Lead | 61 | Data owner signature | Hold dependent loads | Not started
63 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-51:00 | 45 | Extract final Business partners — customers from legacy | Data Migration Lead | 62 | Extract record count logged | Re-extract from snapshot | Not started
64 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-50:15 | 45 | Load Business partners — customers into S/4HANA | Data Migration Lead | 63 | Load log: 0 errors | Delete loaded records and reload | Not started
65 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-49:30 | 45 | Reconcile Business partners — customers (counts and values) | Data Migration Lead | 64 | Reconciliation within tolerance | Correct and reload delta | Not started
66 | 3. Data Migration | Pre-cutover (T-72h to T-48h) | T-48:45 | 45 | Business sign-off on Business partners — customers | Data Migration Lead | 65 | Data owner signature | Hold dependent loads | Not started
67 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-48:00 | 45 | Extract final Business partners — suppliers from legacy | Data Migration Lead | 66 | Extract record count logged | Re-extract from snapshot | Not started
68 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-47:15 | 45 | Load Business partners — suppliers into S/4HANA | Data Migration Lead | 67 | Load log: 0 errors | Delete loaded records and reload | Not started
69 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-46:30 | 45 | Reconcile Business partners — suppliers (counts and values) | Data Migration Lead | 68 | Reconciliation within tolerance | Correct and reload delta | Not started
70 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-45:45 | 45 | Business sign-off on Business partners — suppliers | Data Migration Lead | 69 | Data owner signature | Hold dependent loads | Not started
71 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-45:00 | 45 | Extract final Material masters from legacy | Data Migration Lead | 70 | Extract record count logged | Re-extract from snapshot | Not started
72 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-44:15 | 45 | Load Material masters into S/4HANA | Data Migration Lead | 71 | Load log: 0 errors | Delete loaded records and reload | Not started
73 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-43:30 | 45 | Reconcile Material masters (counts and values) | Data Migration Lead | 72 | Reconciliation within tolerance | Correct and reload delta | Not started
74 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-42:45 | 45 | Business sign-off on Material masters | Data Migration Lead | 73 | Data owner signature | Hold dependent loads | Not started
75 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-42:00 | 45 | Extract final Open accounts receivable items from legacy | Data Migration Lead | 74 | Extract record count logged | Re-extract from snapshot | Not started
76 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-41:15 | 45 | Load Open accounts receivable items into S/4HANA | Data Migration Lead | 75 | Load log: 0 errors | Delete loaded records and reload | Not started
77 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-40:30 | 45 | Reconcile Open accounts receivable items (counts and values) | Data Migration Lead | 76 | Reconciliation within tolerance | Correct and reload delta | Not started
78 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-39:45 | 45 | Business sign-off on Open accounts receivable items | Data Migration Lead | 77 | Data owner signature | Hold dependent loads | Not started
79 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-39:00 | 45 | Extract final Open accounts payable items from legacy | Data Migration Lead | 78 | Extract record count logged | Re-extract from snapshot | Not started
80 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-38:15 | 45 | Load Open accounts payable items into S/4HANA | Data Migration Lead | 79 | Load log: 0 errors | Delete loaded records and reload | Not started
81 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-37:30 | 45 | Reconcile Open accounts payable items (counts and values) | Data Migration Lead | 80 | Reconciliation within tolerance | Correct and reload delta | Not started
82 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-36:45 | 45 | Business sign-off on Open accounts payable items | Data Migration Lead | 81 | Data owner signature | Hold dependent loads | Not started
83 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-36:00 | 45 | Extract final Fixed assets & depreciation from legacy | Data Migration Lead | 82 | Extract record count logged | Re-extract from snapshot | Not started
84 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-35:15 | 45 | Load Fixed assets & depreciation into S/4HANA | Data Migration Lead | 83 | Load log: 0 errors | Delete loaded records and reload | Not started
85 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-34:30 | 45 | Reconcile Fixed assets & depreciation (counts and values) | Data Migration Lead | 84 | Reconciliation within tolerance | Correct and reload delta | Not started
86 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-33:45 | 45 | Business sign-off on Fixed assets & depreciation | Data Migration Lead | 85 | Data owner signature | Hold dependent loads | Not started
87 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-33:00 | 45 | Extract final GL balances & open purchase/sales orders from legacy | Data Migration Lead | 86 | Extract record count logged | Re-extract from snapshot | Not started
88 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-32:15 | 45 | Load GL balances & open purchase/sales orders into S/4HANA | Data Migration Lead | 87 | Load log: 0 errors | Delete loaded records and reload | Not started
89 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-31:30 | 45 | Reconcile GL balances & open purchase/sales orders (counts and values) | Data Migration Lead | 88 | Reconciliation within tolerance | Correct and reload delta | Not started
90 | 3. Data Migration | Cutover execution (T-48h to T-24h) | T-30:45 | 45 | Business sign-off on GL balances & open purchase/sales orders | Data Migration Lead | 89 | Data owner signature | Hold dependent loads | Not started
91 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-54:00 | 35 | Close legacy sub-ledgers for cutover period | Finance Lead | — | Period close report | Re-open period | Not started
92 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-53:25 | 35 | Run legacy AP payment run (final) | Finance Lead | 91 | Payment file sent to bank | Cancel payment run | Not started
93 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-52:50 | 35 | Freeze legacy AR receipts posting | Finance Lead | 92 | Posting lock confirmed | Unfreeze | Not started
94 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-52:15 | 35 | Run legacy depreciation for final period | Finance Lead | 93 | Depreciation log | Reverse run | Not started
95 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-51:40 | 35 | Run legacy GR/IR clearing | Finance Lead | 94 | Clearing report | Reverse clearing | Not started
96 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-51:05 | 35 | Run legacy foreign currency revaluation | Finance Lead | 95 | Revaluation log | Reverse postings | Not started
97 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-50:30 | 35 | Extract legacy trial balance (final) | Finance Lead | 96 | Signed trial balance | Re-extract | Not started
98 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-49:55 | 35 | Extract legacy open item listings | Finance Lead | 97 | AR/AP aged listings | Re-extract | Not started
99 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-49:20 | 35 | Agree cut-off for inventory valuation | Finance Lead | 98 | Stock valuation report | Re-count | Not started
100 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-48:45 | 35 | Open first posting period in S/4HANA | Finance Lead | 99 | OB52 settings logged | Close period | Not started
101 | 4. Finance & Period-End | Pre-cutover (T-72h to T-48h) | T-48:10 | 35 | Configure exchange rates for go-live date | Finance Lead | 100 | Rates table loaded | Reload rates | Not started
102 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-47:35 | 35 | Reconcile opening trial balance to legacy | Finance Lead | 101 | Variance = 0 | Correct opening entries | Not started
103 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-47:00 | 35 | Reconcile AR control account to open items | Finance Lead | 102 | Variance = 0 | Reload AR items | Not started
104 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-46:25 | 35 | Reconcile AP control account to open items | Finance Lead | 103 | Variance = 0 | Reload AP items | Not started
105 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-45:50 | 35 | Reconcile asset register to GL | Finance Lead | 104 | Variance = 0 | Reload assets | Not started
106 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-45:15 | 35 | Reconcile inventory value to GL | Finance Lead | 105 | Variance within tolerance | Adjust and repost | Not started
107 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-44:40 | 35 | Validate tax codes and tax reporting | Finance Lead | 106 | Test tax return output | Revert tax config | Not started
108 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-44:05 | 35 | Validate bank accounts and house banks | Finance Lead | 107 | Bank master check | Correct masters | Not started
109 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-43:30 | 35 | Post test journal and reverse | Finance Lead | 108 | Document numbers logged | n/a | Not started
110 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-42:55 | 35 | Run test payment proposal (no execution) | Finance Lead | 109 | Proposal list correct | Fix vendor masters | Not started
111 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-42:20 | 35 | Validate intercompany settings | Finance Lead | 110 | IC test posting | Revert config | Not started
112 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-41:45 | 35 | Validate cost allocation cycles | Finance Lead | 111 | Test cycle run | Fix cycles | Not started
113 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-41:10 | 35 | Validate financial statement version | Finance Lead | 112 | Balance sheet output | Fix FSV | Not started
114 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-40:35 | 35 | CFO sign-off on opening balances | Finance Lead | 113 | CFO signature | No-Go at checkpoint 2 | Not started
115 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-40:00 | 35 | Confirm audit trail of migration postings | Finance Lead | 114 | Audit pack filed | Rebuild evidence | Not started
116 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-39:25 | 35 | Brief AP / AR teams on day-1 procedures | Finance Lead | 115 | Attendance log | Floor-walker support | Not started
117 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-38:50 | 35 | Confirm first S/4HANA payment run schedule | Finance Lead | 116 | Schedule approved | Manual payments | Not started
118 | 4. Finance & Period-End | Cutover execution (T-48h to T-24h) | T-38:15 | 35 | Confirm month-end close calendar for first period | Finance Lead | 117 | Calendar published | Extend close | Not started
119 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-36:00 | 30 | Switch Bank (payments & statements) interface to S/4HANA endpoints | Integration Lead | — | Endpoint config logged | Re-point to legacy | Not started
120 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-35:30 | 30 | Smoke test Bank (payments & statements) end to end | Integration Lead | 119 | Test message processed | Hold interface, process manually | Not started
121 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-35:00 | 30 | Enable monitoring for Bank (payments & statements) | Integration Lead | 120 | Alert rule active | Manual message checks | Not started
122 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-34:30 | 30 | Switch Customer EDI orders interface to S/4HANA endpoints | Integration Lead | 121 | Endpoint config logged | Re-point to legacy | Not started
123 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-34:00 | 30 | Smoke test Customer EDI orders end to end | Integration Lead | 122 | Test message processed | Hold interface, process manually | Not started
124 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-33:30 | 30 | Enable monitoring for Customer EDI orders | Integration Lead | 123 | Alert rule active | Manual message checks | Not started
125 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-33:00 | 30 | Switch Supplier EDI / procurement network interface to S/4HANA endpoints | Integration Lead | 124 | Endpoint config logged | Re-point to legacy | Not started
126 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-32:30 | 30 | Smoke test Supplier EDI / procurement network end to end | Integration Lead | 125 | Test message processed | Hold interface, process manually | Not started
127 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-32:00 | 30 | Enable monitoring for Supplier EDI / procurement network | Integration Lead | 126 | Alert rule active | Manual message checks | Not started
128 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-31:30 | 30 | Switch Payroll interface to S/4HANA endpoints | Integration Lead | 127 | Endpoint config logged | Re-point to legacy | Not started
129 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-31:00 | 30 | Smoke test Payroll end to end | Integration Lead | 128 | Test message processed | Hold interface, process manually | Not started
130 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-30:30 | 30 | Enable monitoring for Payroll | Integration Lead | 129 | Alert rule active | Manual message checks | Not started
131 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-30:00 | 30 | Switch CRM interface to S/4HANA endpoints | Integration Lead | 130 | Endpoint config logged | Re-point to legacy | Not started
132 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-29:30 | 30 | Smoke test CRM end to end | Integration Lead | 131 | Test message processed | Hold interface, process manually | Not started
133 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-29:00 | 30 | Enable monitoring for CRM | Integration Lead | 132 | Alert rule active | Manual message checks | Not started
134 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-28:30 | 30 | Switch Tax engine interface to S/4HANA endpoints | Integration Lead | 133 | Endpoint config logged | Re-point to legacy | Not started
135 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-28:00 | 30 | Smoke test Tax engine end to end | Integration Lead | 134 | Test message processed | Hold interface, process manually | Not started
136 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-27:30 | 30 | Enable monitoring for Tax engine | Integration Lead | 135 | Alert rule active | Manual message checks | Not started
137 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-27:00 | 30 | Switch Warehouse management interface to S/4HANA endpoints | Integration Lead | 136 | Endpoint config logged | Re-point to legacy | Not started
138 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-26:30 | 30 | Smoke test Warehouse management end to end | Integration Lead | 137 | Test message processed | Hold interface, process manually | Not started
139 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-26:00 | 30 | Enable monitoring for Warehouse management | Integration Lead | 138 | Alert rule active | Manual message checks | Not started
140 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-25:30 | 30 | Switch Data warehouse / BI interface to S/4HANA endpoints | Integration Lead | 139 | Endpoint config logged | Re-point to legacy | Not started
141 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-25:00 | 30 | Smoke test Data warehouse / BI end to end | Integration Lead | 140 | Test message processed | Hold interface, process manually | Not started
142 | 5. Integrations & Interfaces | Cutover execution (T-48h to T-24h) | T-24:30 | 30 | Enable monitoring for Data warehouse / BI | Integration Lead | 141 | Alert rule active | Manual message checks | Not started
143 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-48:00 | 25 | Load production business roles | Security Lead | — | Role count matches design | Re-import roles | Not started
144 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-47:35 | 25 | Assign roles to business users | Security Lead | 143 | Assignment report | Remove assignments | Not started
145 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-47:10 | 25 | Run segregation-of-duties conflict check | Security Lead | 144 | Zero unmitigated critical conflicts | Remove conflicting roles | Not started
146 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-46:45 | 25 | Approve SoD mitigating controls | Security Lead | 145 | Control owner sign-off | Remove access | Not started
147 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-46:20 | 25 | Configure firefighter / emergency access | Security Lead | 146 | Firefighter IDs tested | Manual emergency process | Not started
148 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-45:55 | 25 | Remove project team access from production | Security Lead | 147 | Access report clean | Time-boxed re-grant | Not started
149 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-45:30 | 25 | Configure password and MFA policies | Security Lead | 148 | Policy check | Revert policy | Not started
150 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-45:05 | 25 | Validate external user access (suppliers/partners) | Security Lead | 149 | Test login | Disable external access | Not started
151 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-44:40 | 25 | Lock default and technical accounts | Security Lead | 150 | Account lock report | n/a | Not started
152 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-44:15 | 25 | Enable security audit logging | Security Lead | 151 | Audit log active | Re-enable | Not started
153 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-43:50 | 25 | Validate data privacy / masking settings | Security Lead | 152 | Masking test | Restrict access | Not started
154 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-43:25 | 25 | Validate authorisations for key processes | Security Lead | 153 | Test user walkthrough | Adjust role | Not started
155 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-43:00 | 25 | Confirm access request process for hypercare | Security Lead | 154 | Process published | Manual approvals | Not started
156 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-42:35 | 25 | Sign off user access review | Security Lead | 155 | Security lead signature | Hold business access | Not started
157 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-42:10 | 25 | Confirm legacy access set to read-only | Security Lead | 156 | Legacy role report | Restore write access | Not started
158 | 6. Security & Access | Cutover execution (T-48h to T-24h) | T-41:45 | 25 | Brief service desk on access issues | Security Lead | 157 | Briefing log | Escalate to security | Not started
159 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-24:00 | 30 | Confirm end-user training completion > 90% | Change Lead | — | LMS report | Targeted catch-up sessions | Not started
160 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-23:30 | 30 | Distribute day-1 quick reference guides | Change Lead | 159 | Distribution log | Re-send | Not started
161 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-23:00 | 30 | Confirm super-user floor-walker rota | Change Lead | 160 | Rota published | Add project staff | Not started
162 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-22:30 | 30 | Confirm business contingency procedures | Change Lead | 161 | Procedures signed off | Manual workarounds | Not started
163 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-22:00 | 30 | Brief customer service on go-live changes | Change Lead | 162 | Briefing log | Holding script | Not started
164 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-21:30 | 30 | Notify key customers of any order cut-off | Change Lead | 163 | Customer emails sent | Account manager calls | Not started
165 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-21:00 | 30 | Notify key suppliers of PO / invoice changes | Change Lead | 164 | Supplier emails sent | Buyer calls | Not started
166 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-20:30 | 30 | Notify banks of payment file changes | Change Lead | 165 | Bank confirmation | Manual payments | Not started
167 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-20:00 | 30 | Confirm warehouse shipping cut-off executed | Change Lead | 166 | Shipping report | Manual shipments | Not started
168 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-19:30 | 30 | Run business verification scripts (order-to-cash) | Change Lead | 167 | Scripts passed | Defect triage / No-Go | Not started
169 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-19:00 | 30 | Run business verification scripts (procure-to-pay) | Change Lead | 168 | Scripts passed | Defect triage / No-Go | Not started
170 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-18:30 | 30 | Run business verification scripts (record-to-report) | Change Lead | 169 | Scripts passed | Defect triage / No-Go | Not started
171 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-18:00 | 30 | Run business verification scripts (plan-to-produce) | Change Lead | 170 | Scripts passed | Defect triage / No-Go | Not started
172 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-17:30 | 30 | Collect process owner sign-offs | Change Lead | 171 | All owners signed | No-Go at checkpoint 3 | Not started
173 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-17:00 | 30 | Send go-live welcome message to users | Change Lead | 172 | Message sent | Delay message | Not started
174 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-16:30 | 30 | Open hypercare service desk channel | Change Lead | 173 | Channel live | Email fallback | Not started
175 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-16:00 | 30 | Collect day-1 user feedback pulse | Change Lead | 174 | Pulse results | n/a | Not started
176 | 7. Business Readiness & Comms | Verification & Go/No-Go (T-24h to T-0) | T-15:30 | 30 | Publish known issues and workarounds list | Change Lead | 175 | List published | n/a | Not started
177 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-70:00 | 30 | Announce legacy transaction freeze | Legacy Systems Lead | — | Freeze notice sent | Lift freeze | Not started
178 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-69:30 | 30 | Apply legacy posting freeze | Legacy Systems Lead | 177 | Posting lock confirmed | Unlock postings | Not started
179 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-69:00 | 30 | Stop legacy inbound interfaces | Legacy Systems Lead | 178 | Interface status stopped | Restart interfaces | Not started
180 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-68:30 | 30 | Drain legacy outbound queues | Legacy Systems Lead | 179 | Queues empty | Reprocess queue | Not started
181 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-68:00 | 30 | Archive legacy final reports | Legacy Systems Lead | 180 | Report archive ID | Re-run reports | Not started
182 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-67:30 | 30 | Set legacy ERP to read-only | Legacy Systems Lead | 181 | Read-only roles applied | Restore write access | Not started
183 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-67:00 | 30 | Retain legacy rollback readiness until PONR | Legacy Systems Lead | 182 | Rollback checklist ready | Execute rollback | Not started
184 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-66:30 | 30 | Confirm legacy data retention obligations | Legacy Systems Lead | 183 | Retention plan approved | Extend retention | Not started
185 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-66:00 | 30 | Redirect legacy URLs / shortcuts to S/4HANA | Legacy Systems Lead | 184 | Redirect tested | Restore shortcuts | Not started
186 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-65:30 | 30 | Disable legacy batch schedules permanently | Legacy Systems Lead | 185 | Schedule removed | Restore schedule | Not started
187 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-65:00 | 30 | Confirm legacy licence end dates | Legacy Systems Lead | 186 | Licence schedule | Extend licence | Not started
188 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-64:30 | 30 | Plan legacy decommission date | Legacy Systems Lead | 187 | Date approved | Re-plan | Not started
189 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-64:00 | 30 | Hand legacy read-only access to audit | Legacy Systems Lead | 188 | Audit access confirmed | n/a | Not started
190 | 8. Legacy Freeze & Decommission | Pre-cutover (T-72h to T-48h) | T-63:30 | 30 | Sign off legacy freeze completion | Legacy Systems Lead | 189 | Legacy lead signature | n/a | Not started
191 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+00:00 | 60 | Start hypercare war room | Hypercare Lead | — | War room staffed | Extend cutover team | Not started
192 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+02:00 | 60 | Monitor first business transactions live | Hypercare Lead | 191 | First orders/invoices posted | Manual processing | Not started
193 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+04:00 | 60 | Monitor interface queues every hour | Hypercare Lead | 192 | Queue report | Reprocess | Not started
194 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+06:00 | 60 | Monitor background jobs first run | Hypercare Lead | 193 | Job log clean | Re-run jobs | Not started
195 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+08:00 | 60 | Triage P1/P2 incidents within SLA | Hypercare Lead | 194 | Incident log | Escalate to vendor | Not started
196 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+10:00 | 60 | Daily hypercare stand-up | Hypercare Lead | 195 | Stand-up notes | n/a | Not started
197 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+12:00 | 60 | Daily executive hypercare report | Hypercare Lead | 196 | Report sent | n/a | Not started
198 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+14:00 | 60 | Track business KPIs vs baseline (orders, invoices, shipments) | Hypercare Lead | 197 | KPI dashboard | Contingency procedures | Not started
199 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+16:00 | 60 | Run first daily close | Hypercare Lead | 198 | Daily close checklist | Manual reconciliation | Not started
200 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+18:00 | 60 | Run first payment run in S/4HANA | Hypercare Lead | 199 | Payment file accepted | Manual payments | Not started
201 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+20:00 | 60 | Run first billing run | Hypercare Lead | 200 | Billing documents posted | Manual invoices | Not started
202 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+22:00 | 60 | Run first MRP run | Hypercare Lead | 201 | MRP results reviewed | Manual planning | Not started
203 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+24:00 | 60 | Validate first bank statement import | Hypercare Lead | 202 | Statement posted | Manual posting | Not started
204 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+26:00 | 60 | Validate first payroll interface | Hypercare Lead | 203 | Payroll posting reconciled | Manual journal | Not started
205 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+28:00 | 60 | Review access issues and adjust roles | Hypercare Lead | 204 | Access log | Firefighter access | Not started
206 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+30:00 | 60 | Review performance hot spots | Hypercare Lead | 205 | Performance report | Tune / scale | Not started
207 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+32:00 | 60 | Publish daily known-issues update | Hypercare Lead | 206 | Update published | n/a | Not started
208 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+34:00 | 60 | Confirm defect fix transport process | Hypercare Lead | 207 | Emergency CAB active | Freeze changes | Not started
209 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+36:00 | 60 | Run first week-end close review | Hypercare Lead | 208 | Review notes | n/a | Not started
210 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+38:00 | 60 | Run first month-end close | Hypercare Lead | 209 | Close checklist | Extend close calendar | Not started
211 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+40:00 | 60 | Measure hypercare exit criteria | Hypercare Lead | 210 | Exit criteria scorecard | Extend hypercare | Not started
212 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+42:00 | 60 | Hand over to steady-state support | Hypercare Lead | 211 | Handover sign-off | Extend hypercare | Not started
213 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+44:00 | 60 | Close cutover risks and issues | Hypercare Lead | 212 | RAID closed | Transfer to BAU RAID | Not started
214 | 9. Hypercare Handover | Go-live & hypercare (T-0 onward) | T+46:00 | 60 | Hypercare exit sign-off by sponsor | Hypercare Lead | 213 | Sponsor signature | Extend hypercare | Not started

## Go-No-Go
Checkpoint | When | Criteria | Decision owner | Decision (Go / No-Go) | Notes
1. Readiness | T-72h | Runbook frozen · owners named · mock cutover lessons closed · transports frozen | Steering committee
2. Data loaded | T-24h | All migration objects reconciled · opening balances signed by CFO · interfaces smoke-tested | Executive sponsor
3. Business verification | T-2h | All verification scripts passed · process owners signed · no open P1 defects | Executive sponsor
Point of no return | T-0 | All checkpoint criteria green · rollback window closed | Executive sponsor